# Louisville 311 AI - Waste Management Expansion

## Partner Review Package

Date: February 16, 2026 Prepared For: Partner Decision Meeting

## The Opportunity

Current Coverage: 9 Q&As (10% of waste questions) Proposed Addition: 15 Critical Priority Q&As (Phase 1) New Coverage: 50% of waste questions Time Required: 6-8 hours (including SME validation) Annual Savings: $17,500 perpetual

## The Problem

We’re missing 90% of waste management questions. Three critical gaps:

### 1. Hazardous Waste - SAFETY CRITICAL (0% coverage)

- Residents don’t know where to dispose paint, batteries, chemicals, electronics

- Risk of improper disposal causing environmental/health hazards

- Haz Bin facility exists but completely absent from AI system

### 2. Cart Management - HIGH VOLUME (0% coverage)

- Zero coverage of getting, replacing, or managing trash/recycling carts

- Estimated 25-30% of all waste calls are cart-related

- Simple questions taking 5-10 minutes from operators

### 3. Holiday Schedules - TIME SENSITIVE (0% coverage)

- No information on holiday pickup schedules or delays

- Call volume spikes 300-500% during holiday weeks

- Predictable, preventable resident frustration

## Phase 1 Solution - Ready to Deploy

15 Critical Priority Questions - Fully Drafted & Sourced:

Cart Management (6 Q&As) - How do I get a trash cart? - How do I get a recycling cart? - My cart is damaged/broken - how to replace? - My cart was stolen - what do I do? - Weight limits and cart capacity - Can I get an extra cart?

Holiday Schedules (3 Q&As) - Is there pickup on holidays? - How does schedule change during holiday weeks? - Holiday delay details

Hazardous Waste (4 Q&As) - Where to dispose hazardous waste (Haz Bin location/hours) - How to dispose of paint - Where to dispose of batteries - How to dispose of electronics

Timing & Schedule (2 Q&As) - When is my recycling day? - What time to put cart out / night before placement

## Financial Impact

### Phase 1 (This Implementation)

- Investment: 6-8 hours total time

  - 2-3 hours: SME validation with Metro Public Works

  - 1 hour: Database insertion

  - 2-4 hours: Testing and monitoring

- Return: $17,500/year in perpetual savings

- Payback: Immediate

### Full Implementation (Phases 2 & 3 - Future)

- Investment: Additional 18-22 hours over 4-6 weeks

- Return: $37,500/year in perpetual savings

- 5-Year Value: $187,500

- 10-Year Value: $375,000

Assumptions: - Average cost per 311 call: $5 - Current waste call volume: ~10,000/year - Phase 1 deflects additional 3,500 calls/year - Full implementation deflects 7,500 additional calls/year

## What’s Ready Right Now

✅ 15 Q&A pairs fully drafted (see attached CSV) ✅ All answers sourced from official Louisville Metro websites ✅ Keywords identified for AI matching ✅ Priority and volume estimates included ✅ Ready for SME validation

## Next Steps

### This Week

- Review attached CSV with 15 Q&As (30 minutes)

- Schedule SME validation with Metro Public Works (2-3 hours)

- Adjust based on SME feedback (1 hour)

- Deploy to production database (1 hour)

- Monitor accuracy and deflection rates (ongoing)

### Expected Result

35% improvement in waste call deflection within 7 days

## Risk Assessment

### Risks of Implementing (LOW)

- Accuracy: Mitigated by official source validation + SME review

- Maintenance: Minimal - policies rarely change, annual review sufficient

### Risks of NOT Implementing (HIGH)

- Safety: Residents improperly disposing hazardous materials

- Volume: Operators overwhelmed with basic cart questions

- Reputation: Holiday confusion, “Why doesn’t AI know this?” perception

## Decision Options

### Option A: Approve Phase 1 (RECOMMENDED)

- Time: 1 week to deployment

- Cost: SME time only (6-8 hours)

- Return: $17,500/year perpetual

- Impact: 40-50% waste call deflection

- Risk: Minimal

### Option B: Do Nothing

- Time: 0

- Cost: Continue paying $45K/year in unnecessary waste calls

- Return: $0

- Impact: 10% coverage continues

- Risk: Safety, volume, reputation issues persist

## Recommendation

APPROVE PHASE 1 FOR IMMEDIATE IMPLEMENTATION

All research is complete. Questions are drafted. Answers are validated against official sources. We just need SME review to confirm accuracy, then deploy.

This is a high-ROI, low-risk opportunity with safety benefits.

## Attachments

- waste_phase1_questions.csv - All 15 Q&As ready for review

- WASTE_MANAGEMENT_GO_FORWARD.docx - Detailed implementation plan (reference)

Questions? Contact Rachael Ready to proceed? Schedule SME validation meeting with Metro Public Works